## Sheet1
MEMBER | WEEK1 | WEEK2 | WEEK3 | WEEK4 | WEEK5 | WEEK6 | MEMBER TOTAL
Kareem | 8 | 9 | 8.5 | 4 | 7 | 13 | 49.5
Jake | 7 | 9 | 10 | 11.5 | 8 | 7 | 52.5
Mamoun | 4.5 | 8.5 | 5 | 10 | 11.5 | 12 | 51.5
Quentin | 5 | 7 | 9 | 9 | 10 | 10 | 50
Tristan | 5 | 9 | 8 | 11 | 10 | 11 | 54
Alexis | 4.5 | 7 | 11 | 10.5 | 10 | 11 | 54
Ben | 7 | 13 | 10 | 10 | 7 | 6.5 | 53.5
Richie | 4.5 | 4 | 11 | 9 | 7 | 15 | 50.5
WEEKLY TOTAL | 45.5 | 66.5 | 72.5 | 75 | 70.5 | 85.5 | 415.5
WEEK1
Kareem | WEEK1: Organized and held 1 hour team meeting, prepared Gantt chart, presentation and edited
Jake | WEEK1: 4 hours writing the constraints document and helping others set up their documents + 3 hours preparing them for submission
Tristan | WEEK1: 4.5 hours writing the requirements document + 0.5 hour writing my section in the capabilities document
Quentin | WEEK1: 4 hours writing the systems document + 0.5 hour writing my section in the capabilities document + 0.5 hours preparing for the presentation
Alexis | WEEK1: 4 hours writing the requirements document + 0.5 hour writing my section in the capabilities document
Mamoun | WEEK1: 4 hours writing the requirements document and capabilities section + 0.5 hour preparing for the presentation
Ben | WEEK1: 5 hours writing the System document and Capabilities document, 1 hour delegating presentation sections and preparing for the presentation, 1 hour brainstorming hardware ideas.
Richie | WEEK1: 4 hours writing the requirements document + 0.5 hour writing my section in the capabilities document
WEEK2
Kareem | WEEK1: Re-flashed all EV3s, prepared weekly plan, worked with Jake on Multi-brick test and parallel vs sequential polling ultrasonic sensor test. Helped Alexis and Tristan with software architecture. Updated Gantt chart and presentation
Jake | WEEK1: 2 hours porting Constraints, System and Requirement Documents into LaTeX + 0.5 hour Creating the Budget Document in LaTeX + 3 hours Creating the Testing, Hardware and Software Templates and working on the Brick Test Document and Wheels Test Document + 3.5 hours helping finalise documnents
Tristan | WEEK1: 4 hours for the API research of the software document + 4 hours working on the flowchart and class hierarchy
Alexis | WEEK1: 2 hours for the API research of the software document + 5 hours working on the flowchart and class hierarchy
Mamoun | WEEK1: 2 hours for building the test robot model for locomoion testing + 2 hours testing different locomotion designs + 4 hours working on Wheels testing document + 0.5 hour porting locomotion test results to the Hardware Document
Quentin | WEEK1: 5 hours writing the hardware document, sketching designs and 2 hours in the lab building different designs for grabbers and seeing which ones would be the most feasible, as well as taking note of what pieces we have in our kits.
Ben | WEEK1: 8 hours writing the hardware document, 2 hours constructing a hybrid design, 2 hours setting up initial hardware documents and instructions, 1 hour delegating work and instructing team members.
Richie | WEEK1: 3 hours building the test robot model for locomotion testing + 1 hour writing hardware locomotion document.
WEEK3
Kareem | WEEK1: Helped software team finalize main algorithm, helped hardware team with a few designs. Finished Gantt Chart
Jake | WEEK1: 1 hour building a grabber + 1 hour changing the Budget document to a spreadsheet and adding the sketches to the hardware doc + 6 hours editing hardware designs testing docs + 2 hours finalising docs/presentation
Tristan | WEEK1: 1 hour software meeting + 7 hours coding and testing the localization routine
Alexis | WEEK1: 2 hours testing WiFi code and writing test document + 1 hour software meeting + 1 hour coding dynamic search algorithm + 3.5 testing localization routines + 1 hour coding bumper localization algorithm + 1 writing localization testing document + 1.5 hours updating class hierarchy in the software document
Mamoun | WEEK1: 4 hours testing the rear wheel drive and different third wheel designs + 1 hour editing testing document
Quentin | WEEK1: 5 hours Saturday and 4 hours Sunday constructing and testing various designs including the static collector and static grabber, the dual brick chassis and the single brick chassis. All were documented and analyzed for best possible options.
Ben | WEEK1: 7 hours constructing various components, 2 hours working on the hardware document, and 1 hour instructing team members and preparing for the presentation.
Richie | WEEK1: 9 hours building different designs using treads, wheels, balls, and gears + 2 hours writing testing documentation.
WEEK4
Kareem | WEEK1: More updates to Gantt chart, worked on logging framework
Jake | WEEK1: 0.75 hours starting the poster + 1.25 filling out the localization timing test + 5 hours working on the LDD + 2 hours working on the navigation test + 2.5 hours editing presentation
Tristan | WEEK1: Software localization completed. Navigation methods. WiFi Connection integration.
Alexis | WEEK1: Software localization completed. Navigation methods. WiFi Connection integration.
Mamoun | WEEK1: 5 hours writing test documents + 5 hours running multiple tests
Quentin | WEEK1: 5 hours constructing and stringing Hardware versions 2.5 and 2.55, 1 hour re allocating blocks to different kits, 3 hours testing navigation for versions 2.5 and 2.55
Ben | WEEK1: 7 hours building hardware versions 1.5, 2, and 2.5, 3 hours writing documentation (various testing documents, and the hardware document)
Richie | WEEK1: 5 hours writing test documents + 4 hours running multiple tests
WEEK5
Kareem | WEEK1: Software: Helped with search algorithm, Documentation: Gantt updates and Presentation
Jake | WEEK1: Documentation: Helped write out the grabber test document, the builder integration test and calibration document, started the final report and worked on the powerpoint/uploaded docs
Tristan | WEEK1: Software: Completed localization, completed WiFi connection, wrote the search algorithm for the demo and started working on obstacle avoidance.
Alexis | WEEK1: Software: Completed localization, completed WiFi connection, wrote the search algorithm for the demo and started working on obstacle avoidance.
Mamoun | WEEK1: Testing: Helped with wheel radius and width calibration Documentation: Helped write out the builder integration test document and the calibration document
Quentin | WEEK1: Spent 3.5 hours writing pick up block code and testing documents, as well as did various tests to ensure proper block pick up. In addition spent an hour revamping hardware model to 3.01 with a working lifter. Spent 5.5 hours writing documentation for final wheel radius and track width calibration tests and testing for these.
Ben | WEEK1: 2 hours working with hardware iterations, 2 hours working on documentation, 1.5 hours instructing and conferring with team members, 1 hour planning an odometry correction algorithm, and 0.5 hours preparing for the presentation
Richie | WEEK1: Documentation: Helped write out integration test document
WEEK6
Kareem | WEEK1: Helped with poster design, begin editting some documents and assisted with final software tweaks and testing
Jake | WEEK1: Testing: Helped test odometry correction, avoidance and light sensor. Documentation: Updated LDD and edited documents
Tristan | WEEK1: Wrote obstacle avoidance, implemented odometry correction into the main class and coded the opposite team's zone avoidance.
Alexis | WEEK1: Assembled the code together, improved the search algorithm, worked on obstacle avoidance and odometry correction.
Mamoun | WEEK1: Testing: Tested track width calibration, obstacle avoidance, light sensors in different environments and helped with editing various testing documents.
Quentin | WEEK1: 4 hours for various tests for block pickup and odometry correction and overall testing. 2 hours working on hardware section of poster, 4 hours doing various integration testing and assisting various sub groups
Ben | WEEK1: Wrote odometry correction, performed hardware maintenance, and edited the poster.
Richie | WEEK1: 3 hours testing + 12 hours on poster